## Asset Retirement MProj 24-29
Area Plan Project | Asset Category | Description | Retirement year | Area | New Retirement? | Changes from DTAPR 2023 | Reasons for change | Distribution / Dual Function
PR_1.1.0026 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 928/3 & 929/1 LANE COVE STSS - DALLEY ST ZN | 2025 | Inner Metro | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_1.1.0028A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 9SA & 92P BEACONSFIELD - CAMPBELL ST ZN & BELMORE PK ZN | 2025 | Inner Metro | No | No |  | Dual Function
PR_1.1.0029A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91X/2 & 91Y/2 CHULLORA STSS - MARRICKVILLE ZN | 2028 | Inner Metro | Yes | Yes | Project timing adjustment. | Dual Function
PR_1.1.0030A | 131 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91A/1 & 91B/1 BEACONSFIELD BSP - ST PETERS ZN | 2030 | Inner Metro | Yes | Yes | Project timing adjustment. | Dual Function
PR_1.1.0034A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 92X & 92C CHULLORA STSS - ST PETERS ZN | 2028 | Inner Metro | Yes | Yes | Project timing adjustment. | Dual Function
PR_1.1.0045A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91X/1 & 91Y/1 BEACONSFIELD BSP - MARRICKVILLE ZN | 2028 | Inner Metro | Yes | Yes | Project timing adjustment. | Dual Function
PR_1.1.0110 | 132 kV Underground Cable (Oil Filled Type) x 3 | RETIRE 132KV FEEDERS 91L, 91M & 91M/3 PEAKHURST STS - BUNNERONG STSS | 2024 | Inner Metro | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Dual Function
PR_1.1.0111 | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDERS 9FF BEACONSFIELD BSP - MILL POND RD | 2030 | Inner Metro | Yes | Yes | Project timing adjustment. | Dual Function
PR_1.4.0037A | STS Switchgear 33kV (Oil) - Circuit Breaker x 24 | RETIRE 33KV SWITCHGEAR MEREWETHER 132/33KV STS | 2029 | Lower Hunter Transmission | Yes | Yes | Change of preferred option to address asset condition issues | Distribution
PR_1.4.0037A | STS Switchroom Building | RETIRE 33KV SWITCHGEAR MEREWETHER 132/33KV STS | 2029 | Lower Hunter Transmission | Yes | Yes | Change of preferred option to address asset condition issues | Distribution
PR_2.1.0017 | 132 kV Underground Cable (Oil Filled Type) x 4 | RETIRE 132KV FEEDERS 929/2, 92L/1, 928/1 & 92M/2 SURRY HILLS STS - DALLEY ST ZN | 2026 | Sydney CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0127 | 33 kV Underground Cables (HSL Type) x 6 | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | 33 kV Underground Cables (XLPE Type) x 6 | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | Zone CLC equipment (Mechanical) x 3 | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | Zone General (including spares) | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | Zone Switchgear 11kV (Oil) - Circuit Breakers x 48 | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 6 | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2024 | CBD | No | No |  | Distribution
PR_2.1.0127 | Zone Substation Building | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone CLC equipment (Mechanical) x 3 | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone General (including spares) | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone Switchgear 132kV (Gas) - Circuit Breakers x 7 | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone Switchgear 11kV (Oil) - Circuit Breakers x 53 | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone Transformers - 132/11kV (Gas) - (<=100 MVA) x 1 | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone Transformers - 132/11kV (Oil) - (<=100 MVA) x 3 | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_2.1.0134A | Zone Substation Building | RETIRE DALLEY ST 132/11KV ZN | 2025 | CBD | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1A.0005 | 33 kV Underground Cables (Gas-Filled Type) x 2 | RETIRE DARLINGHURST 33/11KV ZN STAGE 1 & ASSOCIATED 33KV FEEDERS | 2024 | Eastern suburbs | No | No |  | Distribution
PR_3.1A.0005 | Zone CLC equipment (Mechanical) x 3 | RETIRE DARLINGHURST 33/11KV ZN STAGE 1 & ASSOCIATED 33KV FEEDERS | 2024 | Eastern suburbs | No | No |  | Distribution
PR_3.1A.0005 | Zone General (including spares) | RETIRE DARLINGHURST 33/11KV ZN STAGE 1 & ASSOCIATED 33KV FEEDERS | 2024 | Eastern suburbs | No | No |  | Distribution
PR_3.1A.0005 | Zone Switchgear 11kV (Oil) - Circuit Breakers x 13 | RETIRE DARLINGHURST 33/11KV ZN STAGE 1 & ASSOCIATED 33KV FEEDERS | 2024 | Eastern suburbs | No | No |  | Distribution
PR_3.1A.0005 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 2 | RETIRE DARLINGHURST 33/11KV ZN STAGE 1 & ASSOCIATED 33KV FEEDERS | 2024 | Eastern suburbs | No | No |  | Distribution
PR_3.1A.0029A | 33 kV Underground Cables (Gas-Filled Type) x 2 | RETIRE DARLINGHURST 33KV FEEDERS 386 & 389 | 2028 | Eastern suburbs | Yes | Yes | Change of preferred option to address asset condition issues | Distribution
PR_3.1B.0017 | 33 kV Underground Cables (HSL Type) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2029 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1B.0017 | Zone CLC equipment (Mechanical) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2029 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1B.0017 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 25 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2029 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1B.0017 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2029 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1B.0032A | Zone Switchgear 11kV (VCB) - Circuit Breakers x 9 | RETIRE 11KV COMPOUND SWITCHGEAR BOTANY 33/11KV ZN | 2028 | Eastern suburbs | Yes | Yes | Project timing adjustment. | Distribution
PR_3.1B.0034A | Zone Switchgear 33kV (Oil) - Circuit Breaker | RETIRE 33KV SWITCHGEAR SYDNEY DOMESTIC 33/11KV ZN | 2025 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1C.0004 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 33 | RETIRE 11KV SWITCHGEAR SURRY HILLS 33/11KV ZN | 2025 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_3.1C.0030 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 260/1 & 261/1 BEACONSFIELD BSP - ZETLAND ZN | 2025 | Eastern suburbs | No | No |  | Distribution
PR_3.1C.0038A | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDER 264 BEACONSFIELD BSP - KINGSFORD ZN | 2026 | Eastern suburbs | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Dual Function
PR_3.1C.0039A | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDER 265 BUNNERONG NORTH STS - MAROUBRA ZN | 2024 | Eastern suburbs | No | No |  | Dual Function
PR_4.1.0007 | 33 kV Underground Cables (Gas-Filled Type) x 2 | RETIRE 33KV FEEDERS 769 & 770 PEAKHURST STS - BLAKEHURST ZN | 2030 | St George | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.1.0029 | STS Switchgear 33kV (Oil) - Circuit Breaker x 32 | RETIRE 33KV SWITCHGEAR PEAKHURST 132/33KV STS | 2024 | St George | No | No |  | Distribution
PR_4.1.0029 | STS Switchroom Building | RETIRE 33KV SWITCHGEAR PEAKHURST 132/33KV STS | 2024 | St George | No | No |  | Distribution
PR_4.3A.0007 | Zone CLC equipment (Mechanical) x 3 | RETIRE ENFIELD 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0007 | Zone General (including spares) | RETIRE ENFIELD 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0007 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 22 | RETIRE ENFIELD 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0007 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 3 | RETIRE ENFIELD 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0007 | Zone Substation Building | RETIRE ENFIELD 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone CLC equipment (Mechanical) x 2 | RETIRE GREENACRE PARK 132/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone General (including spares) | RETIRE GREENACRE PARK 132/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone Switchgear 132kV (Oil) - Circuit Breaker x 1 | RETIRE GREENACRE PARK 132/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 36 | RETIRE GREENACRE PARK 132/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone Transformers - 132/11kV (Oil) - (<=100 MVA) x 4 | RETIRE GREENACRE PARK 132/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0014 | Zone Substation Building | RETIRE GREENACRE PARK 132/11KV ZN | 2025 | Canterbury Bankstown | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.3A.0019 | Zone General (including spares) | RETIRE DULWICH HILL 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0019 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 32 | RETIRE DULWICH HILL 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0019 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 4 | RETIRE DULWICH HILL 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0019 | Zone Substation Building | RETIRE DULWICH HILL 33/11KV ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3A.0033A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 291 & 292 POTTS HILL ZN - GREENACRE PARK ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.3B.0008 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 15 | RETIRE 11KV SWITCHGEAR MILPERRA 33/11KV ZN | 2027 | Canterbury Bankstown | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.3B.0036A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 282/1 & 283/1 SYDNEY SOUTH BSP - REVESBY ZN | 2024 | Canterbury Bankstown | No | No |  | Distribution
PR_4.4.B.0002 | 33 kV Underground Cables (HSL Type) x 3 | RETIRE 33KV FEEDERS HSL SECTIONS 607, 608 & 609 HOMEBUSH STS - CONCORD ZN | 2026 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.B.0002 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 26 | RETIRE 11KV SWITCHGEAR CONCORD 33/11KV ZN | 2026 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.B.0002 | Zone Substation Building | RETIRE 11KV SWITCHGEAR CONCORD 33/11KV ZN | 2026 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.B.0010 | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDER 90L MASON PARK STSS - HOMEBUSH STS | 2025 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.B.0022A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 923/2 & 924/2 MASON PARK STSS - BURWOOD ZN | 2025 | Inner West | No | No |  | Distribution
PR_4.4.C.0008 | 33 kV Underground Cables (Gas-Filled Type) x 6 | RETIRE 33KV FEEDERS 601, 614, 615/602, 604, 605 HOMEBUSH STS - AUBURN ZN/LIDCOMBE ZN | 2025 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.C.0008 | 33 kV Underground Cables (HSL Type) x 4 | RETIRE 33KV FEEDERS 601, 614, 615 & 602 HOMEBUSH STS - AUBURN ZN/LIDCOMBE ZN | 2025 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.4.C.0009 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 8 | RETIRE 11kV SWITCHGROUP 2 LIDCOMBE 33/11KV ZN | 2025 | Inner West | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_4.5.0006 | 33 kV Underground Cables (HSL Type) x 4 | RETIRE BLACKWATTLE BAY 33/5KV ZN & ASSOCIATED 33KV FEEDERS | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_4.5.0006 | Zone CLC equipment (Mechanical) x 3 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_4.5.0006 | Zone General (including spares) | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_4.5.0006 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 33 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_4.5.0006 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 4 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_4.5.0006 | Zone Substation Building | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2024 | Camperdown Blackwattle Bay | No | No |  | Distribution
PR_5.1.0014 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 9Y7/2 & 9Y9/2 CASTLE COVE ZN - MOSMAN ZN | 2024 | Lower North Shore | No | No |  | Distribution
PR_5.1.0035A | STS Switchgear 33kV (Oil) - Circuit Breaker x 28 | RETIRE 33KV SWITCHGEAR WILLOUGHBY 132/33KV STS | 2029 | Lower North Shore | Yes | Yes | Change of preferred option to address asset condition issues | Distribution
PR_5.1.0035A | STS Switchroom Building | RETIRE 33KV SWITCHGEAR WILLOUGHBY 132/33KV STS | 2029 | Lower North Shore | Yes | Yes | Change of preferred option to address asset condition issues | Distribution
PR_5.2.0019 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 9E1 & 9E2 SYDNEY EAST BSP - KURINGAI STS | 2025 | Upper North Shore | No | No |  | Distribution
PR_7.2.0004 | STS Switchgear 33kV (Oil) - Circuit Breaker x 16 | RETIRE 33KV SWITCHGEAR WARATAH 132/33KV STS | 2025 | Newcastle Ports | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_7.2.0004 | STS Switchgear 132kV (Oil) - Circuit Breaker x 10 | RETIRE 132KV SWITCHGEAR WARATAH 132/33KV STS | 2025 | Newcastle Ports | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_7.2.0004 | STS Transformers - 132/33kV (Oil) - (<=100 MVA) x 6 | RETIRE 132/33KV TRANSFORMERS WARATAH 132/33KV STS | 2025 | Newcastle Ports | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_7.2.0004 | STS Reactors and Capacitors x 1 | RETIRE 33KV CAPACITOR BANK WARATAH 132/33KV STS | 2025 | Newcastle Ports | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_7.3.0016 | STS Switchgear 33kV (Oil) - Circuit Breaker x 6 | RETIRE 33KV SWITCHGEAR STOCKTON BOREHOLE 33KV SS | 2024 | Newcatle Western Corridor | No | No |  | Distribution
PR_7.4.0002 | 33kV Wood Lines Mains Conductor & Accessories | RETIRE 33KV REDUNDANT NETWORK AWABA 132/33KV STS | 2025 | West Lake Macquarie | No | No |  | Distribution
PR_7.6.0014 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 12 | RETIRE 11kV SWITCHGEAR TARRO 33/11KV ZN | 2025 | Maitland | No | No |  | Distribution
PR_8.2.0027 | 33kV Wood Lines Mains Conductor & Accessories | RETIRE 33KV REDUNDANT NETWORK MUSWELLBROOK 132/33KV STS | 2025 | Upper Hunter | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_8.2.0027 | STS Switchgear 33kV (Oil) - Circuit Breaker x 12 | RETIRE 33KV SWITCHGEAR MUSWELLBROOK 132/33KV STS | 2025 | Upper Hunter | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
PR_8.2.0027 | STS Transformers - 132/33kV (Oil) - (>100 MVA) | RETIRE TRANSFORMER 2 MUSWELLBROOK 132/33KV STS | 2025 | Upper Hunter | No | Yes | Project timing adjustment as per forecast project delivery schedule. | Distribution
| Methodology | Cost Benefit analysis carried out for alternative options to satisfy identified needs. Value of unserved energy from an interruption to supply is estimated based on the probabilities of items of equipment being unavailble for service. Other factors considered include safety, environmental risks and change in maintenance costs.
| Additional Notes | The dates listed in the retirement year column are indicative of the electrical disconnection and decommission of the corresponding network assets. This may defer from the dates indicated in Chapters 5, 6 and 7 of the DTAPR document because the latter indicates date expected completion or the date when the network issue is addressed.